## README
PLAN BOARD ¦ CWL-4 ¦ 2026-11 (30 days)
1. One row per PO (Style + PO + Color). Fill the yellow cells once: buyer, CRD, order qty, wash plan start / end, opening balances. Rows 1-7 are headers, data starts at row 8.
2. Every day: Sewing planned delivery and Wash planned production come from the planner. Sewing ACTUAL delivery and Wash ACTUAL production are typed by the monitoring team. Variation and totals are formulas.
3. Do NOT change numbers that were already entered. The script logs every change (old value, new value, who, when), the cell turns red and the dashboard shows the order as "edited".
4. Wash plan start / end, CRD and order qty changes are saved as plan history (version 1, 2, 3 ...). Revising the plan is allowed: the history just keeps the proof.
5. Work sequence = earliest delivery date (CRD) first; same CRD -> first received first (FIFO); then PO. Column "Wash Priority" shows it. Filter / sort by that column.
6. After the wash plan end date, if balance or WIP is still open the row is red flagged (Risk = Yes) and the dashboard reports it as crisis / possible crisis.
7. Month length: change cell B2 (first day of the month). Day blocks beyond the month length go blank; run Plan Board > Setup month to hide them. 28, 29, 30 or 31 days work.
8. Next month: Plan Board > Create next month sheet. It copies this file, keeps only open orders, carries the opening balances and clears the days. Then add the old Sheet ID to Secrets "archive" as YYYY-MM:ID and the new ID to "current".
9. Stage_Log (optional): where the pieces are inside the plant (Receive Store, Wash, Dry Process, QC & Packing ...). Date, Wash_Plant, Style, PO, Color, Stage, Pcs_In, Pcs_Out. A scan system export fits this layout.
10. Share the Sheet as "Anyone with the link" if the dashboard reads it without a service account. Floor staff need Editor access.
Rows whose Style starts with EXAMPLE are ignored by the dashboard.

## Plan_Board
HAMEEM GROUP ¦ E2E Plan Execution (Sewing - Wash) ¦ CWL-4
Month (first day) | 2026-11-01 |  | Wash plant | CWL-4 |  | Days in month |  |  | Do not insert rows above row 8 - the dashboard reads rows 1-6 as headers.
Wash_Plant | Sewing_Unit | Buyer | Style | PO | Item | Color | Season | CRD | Revised_CRD | Order_Qty | Plan_Start | Plan_End | Merchant | Open_Received | Open_Washed | Open_Sew_Var | Open_Wash_Var | First_Received_On | Wash_Reject | Missing_Body | Eff_CRD | Received | Washed | WIP | Balance | First_Receive | Priority | Forecast | Sew_Delay | Risk | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK | SEW_PLAN | SEW_ACT | SEW_VAR | WASH_PLAN | WASH_ACT | WASH_VAR | REMARK
Wash Plant | Sewing Unit | Buyer | Style | PO | Item | Color | Season | CRD Date | Revised CRD | Order Quantity | Wash Plan Start | Wash Plan End | Merchant | Opening Received (before this month) | Opening Washed (before this month) | Sewing Plan Variation (Opening) | Wash Plan Variation (Opening) | First Received On (carry forward) | Wash Reject Qty | Missing Body | Effective CRD | Received from Sewing | Wash Throughput | Wash WIP | Balance to Wash | First Receive Date | Wash Priority (EDD then FIFO) | Forecasted Completion | Sewing Delay Days | Risk (Yes/No) | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks | Sewing Planned Delivery | Sewing Actual Delivery | Variation | Wash Planned Production | Wash Actual Production | Variation | Remarks
Grand Total
CWL-4 | TISWL-01 | Buyer name | EXAMPLE ST-4412 | PO-0001 | Denim Pant | Dark Blue | SP27 | 2026-11-28 |  | 20000 | 2026-11-05 | 2026-11-15 | EXAMPLE - delete me
Formulas:
Forecast = IF(OR([PO]="",[Balance]=0),"",IFERROR(TODAY()+ROUNDUP([Balance]/(SUMIFS([SEW_PLAN]:[REMARK],AF4:IN4,"WASH_ACT")/COUNTIFS(AF4:IN4,"WASH_ACT",[SEW_PLAN]:[REMARK],">0")),0),"no output yet"))
Risk = IF([PO]="","",IF(AND([Balance]>0,OR(AND([Plan_End]<>"",TODAY()>[Plan_End]),AND([Eff_CRD]<>"",[Eff_CRD]-TODAY()<=7))),"Yes","No"))
SEW_VAR = IF(OR(AF3="",AF3>TODAY()),"",IF(AND([SEW_PLAN]="",[SEW_ACT]=""),"",N([SEW_ACT])-N([SEW_PLAN])))
SEW_VAR = IF(OR(AM3="",AM3>TODAY()),"",IF(AND([SEW_PLAN]="",[SEW_ACT]=""),"",N([SEW_ACT])-N([SEW_PLAN])))
WASH_VAR = IF(OR(AF3="",AF3>TODAY()),"",IF(AND([WASH_PLAN]="",[WASH_ACT]=""),"",N([WASH_ACT])-N([WASH_PLAN])))
WASH_VAR = IF(OR(AM3="",AM3>TODAY()),"",IF(AND([WASH_PLAN]="",[WASH_ACT]=""),"",N([WASH_ACT])-N([WASH_PLAN])))

## Plan_History
Timestamp | User | Wash_Plant | Style | PO | Color | Field | Old | New | Version

## Audit_Log
Timestamp | User | Wash_Plant | Style | PO | Color | Field | Date | Old | New | Type | Ack

## Stage_Log
Date | Wash_Plant | Style | PO | Color | Stage | Pcs_In | Pcs_Out | Remarks

## Master_Stage
Stage | Seq
Receive Store | 1
Wash | 2
Dry Process | 3
QC & Packing | 4

## Unit_Master
Wash_Plant | Wet_Capacity_Day | Dry_Capacity_Day | Plant capacity in pcs per day (wet = wash, dry = dry process total). Used for the dashboard forecast.
CWL-4 | 32317 | 14000