## README
WASH & DRY HOURLY LOG - NWL
1. Upload this file to Google Drive and open with Google Sheets (File > Save as Google Sheets).
2. Extensions > Apps Script > paste apps_script/Code.gs > Save > reload. A "Wash Tools" menu appears.
3. Each production day: Wash Tools > Create rows for a day. It fills Date, Hour, Unit and Machine/Process for all 24 hours.
4. Supervisors type only numbers (Input, Output, QC, Defect, Rewash, Downtime). Grey columns are keys - do not edit.
5. Style, PO and Color: pick from the dropdown (comes from Order_Master) or type. Wash type and Downtime reason are dropdowns.
5b. Order_Master: one row per Style + PO + Color (buyer, CRD, order qty, shade dates, merchant). Plan_Start..Plan_End = wash INPUT window; Order_Qty is spread evenly over it to get plan till today. Feeds the dashboard Style details table. Write ALL dates as yyyy-mm-dd.
5c. Daily_Plan (optional): real planned input and output pcs per date per order. Without it the dashboard spreads Order_Qty evenly over Plan_Start..Plan_End.
6. WIP_Log: one row per stage per day with the physical opening WIP. Stage = WASH or a dry process name (exactly as in Master_Process).
7. Master_Machine / Master_Process: plan per hour comes from here. Edit Plan_per_hr for a machine, or set Active = N for a machine that is down for the day.
8. Share this Google Sheet with the dashboard service account as VIEWER. Floor staff get EDITOR access.
8b. Unit_Master: wet and dry capacity per day of the plant (shown on Overview). Allotment (optional): plan pcs allotted to each machine / process per day.
9. Recommended: ONE Google Sheet per wash plant per MONTH (10 sheets). Month end: add the old Sheet ID to Secrets as an archive entry (YYYY-MM:SheetID) and copy this template for the new month.
Rows with "EXAMPLE" in Remarks are ignored by the dashboard - delete them whenever you like.
Hour slots assume the production day starts at Day_Start_Hour in Settings (08:00 default): hours after midnight belong to the same production date.

## Settings
Key | Value | Meaning
Run_Hours | 24 | Hours the plant runs per day (hourly plan = capacity per day / this)
Day_Start_Hour | 8 | Production day start hour (0-23); shifts A/B/C are 8 hours each
Plan_Basis | 100% | 1 = plan at 100% of capacity; 0.85 = plan at 85% load
Target_Pct | 95% | Achievement at/above = green
Alert_Pct | 80% | Achievement below = red
Max_Defect_Pct | 3% | Defect limit (defect pcs / QC inspected pcs) - placeholder, set yours
Max_Rewash_Pct | 2% | Rewash limit (rewash pcs / output pcs) - placeholder, set yours
Output_Lag_Days | 2 | Style details: wash OUTPUT plan starts this many days after the input plan

## Master_Machine
Unit | Machine_ID | Type | Plan_per_hr | Active | Plan_per_hr = unit wash capacity per day / machines / run hours (Capacity_August_2026). It is an average - overwrite per machine when you know the real capacity.
NWL | NWL-FL-01 | F/L | 31.7353 | Y
NWL | NWL-FL-02 | F/L | 31.7353 | Y
NWL | NWL-FL-03 | F/L | 31.7353 | Y
NWL | NWL-FL-04 | F/L | 31.7353 | Y
NWL | NWL-FL-05 | F/L | 31.7353 | Y
NWL | NWL-FL-06 | F/L | 31.7353 | Y
NWL | NWL-FL-07 | F/L | 31.7353 | Y
NWL | NWL-FL-08 | F/L | 31.7353 | Y
NWL | NWL-FL-09 | F/L | 31.7353 | Y
NWL | NWL-FL-10 | F/L | 31.7353 | Y
NWL | NWL-FL-11 | F/L | 31.7353 | Y
NWL | NWL-FL-12 | F/L | 31.7353 | Y
NWL | NWL-FL-13 | F/L | 31.7353 | Y
NWL | NWL-FL-14 | F/L | 31.7353 | Y
NWL | NWL-FL-15 | F/L | 31.7353 | Y
NWL | NWL-FL-16 | F/L | 31.7353 | Y
NWL | NWL-FL-17 | F/L | 31.7353 | Y
NWL | NWL-FL-18 | F/L | 31.7353 | Y
NWL | NWL-FL-19 | F/L | 31.7353 | Y
NWL | NWL-FL-20 | F/L | 31.7353 | Y
NWL | NWL-FL-21 | F/L | 31.7353 | Y
NWL | NWL-FL-22 | F/L | 31.7353 | Y
NWL | NWL-FL-23 | F/L | 31.7353 | Y
NWL | NWL-FL-24 | F/L | 31.7353 | Y
NWL | NWL-FL-25 | F/L | 31.7353 | Y
NWL | NWL-FL-26 | F/L | 31.7353 | Y
NWL | NWL-FL-27 | F/L | 31.7353 | Y
NWL | NWL-FL-28 | F/L | 31.7353 | Y
NWL | NWL-FL-29 | F/L | 31.7353 | Y
NWL | NWL-FL-30 | F/L | 31.7353 | Y
NWL | NWL-FL-31 | F/L | 31.7353 | Y
NWL | NWL-FL-32 | F/L | 31.7353 | Y
NWL | NWL-FL-33 | F/L | 31.7353 | Y
NWL | NWL-FL-34 | F/L | 31.7353 | Y
NWL | NWL-FL-35 | F/L | 31.7353 | Y
NWL | NWL-FL-36 | F/L | 31.7353 | Y
NWL | NWL-FL-37 | F/L | 31.7353 | Y
NWL | NWL-FL-38 | F/L | 31.7353 | Y
NWL | NWL-FL-39 | F/L | 31.7353 | Y
NWL | NWL-AB-01 | Acid B/L | 31.7353 | Y
NWL | NWL-AB-02 | Acid B/L | 31.7353 | Y
NWL | NWL-AB-03 | Acid B/L | 31.7353 | Y
NWL | NWL-AB-04 | Acid B/L | 31.7353 | Y
NWL | NWL-AB-05 | Acid B/L | 31.7353 | Y
NWL | NWL-BL-01 | B/L | 31.7353 | Y
NWL | NWL-BL-02 | B/L | 31.7353 | Y
NWL | NWL-BL-03 | B/L | 31.7353 | Y
NWL | NWL-BL-04 | B/L | 31.7353 | Y
NWL | NWL-BL-05 | B/L | 31.7353 | Y
NWL | NWL-BL-06 | B/L | 31.7353 | Y
NWL | NWL-BL-07 | B/L | 31.7353 | Y

## Master_Process
Unit | Process | Machines | Capacity_per_day | Active

## Lists
Hour slots | Wash types | Wash downtime reasons | Dry downtime reasons | Dry processes
08:00-09:00 | Denim | Machine breakdown | Machine breakdown
09:00-10:00 | Acid | Power / utility | Power / utility
10:00-11:00 | Twill | Water / steam shortage | Waiting for input
11:00-12:00 | Dyeing | Waiting for input | Waiting for material
12:00-13:00 |  | Waiting for chemical | Operator shortage
13:00-14:00 |  | Waiting for dryer / unload | Changeover / setup
14:00-15:00 |  | Shade / quality hold | Quality hold
15:00-16:00 |  | Changeover / cleaning | Other
16:00-17:00 |  | Other
17:00-18:00
18:00-19:00
19:00-20:00
20:00-21:00
21:00-22:00
22:00-23:00
23:00-00:00
00:00-01:00
01:00-02:00
02:00-03:00
03:00-04:00
04:00-05:00
05:00-06:00
06:00-07:00
07:00-08:00

## Order_Master
Wash_Plant | Buyer | Style | PO | Color | Wash_Type | CRD | CRD_Revisions | Updated_CRD | Sewing_Unit | Order_Qty | Plan_Start | Plan_End | Shade_Submit_Date | Shade_Approval_Date | Merchant | Prior_Input | Prior_Output | Remarks
NWL | Buyer name | ST-4412 Dark Stone | PO-0001 | Dark Blue | Denim | 2026-11-20 | 0 |  | TISWL-01 | 20000 | 2026-10-08 | 2026-10-20 | 2026-10-05 |  | Merchant name | 0 | 0 | EXAMPLE - delete me

## Wash_Log
Date | Hour | Unit | Machine_ID | Wash_Type | Style | PO | Color | Input | Output | QC_Inspected | Defect | Rewash | Rewash_Output | Reject | Downtime_Min | Downtime_Reason | Remarks
2026-10-08 | 08:00-09:00 | NWL | NWL-FL-01 | Denim | ST-4412 Dark Stone | PO-0001 | Dark Blue | 120 | 110 | 90 | 2 | 1 | 0 | 0 |  |  | EXAMPLE - delete me

## Dry_Log
Date | Hour | Unit | Process | Style | PO | Color | Input | Output | Defect | Rework | Downtime_Min | Downtime_Reason | Remarks
2026-10-08 | 08:00-09:00 | NWL | Pattern Whisker | ST-4412 Dark Stone | PO-0001 | Dark Blue | 900 | 880 | 15 | 8 |  |  | EXAMPLE - delete me

## Daily_Plan
Date | Wash_Plant | Style | PO | Color | Plan_Input | Plan_Output | Optional. One row per date per order: how many pcs you PLAN to input and to output that day. Orders listed here override the straight-line plan from Order_Master. Dates as yyyy-mm-dd.

## WIP_Log
Date | Unit | Stage | Opening_WIP | Remarks
2026-10-08 | NWL | WASH | 100000 | EXAMPLE - delete me

## Unit_Master
Wash_Plant | Wet_Capacity_Day | Dry_Capacity_Day | Plant total capacity in pcs per day (wet = wash, dry = dry process total, no breakdown). Shown on the dashboard Overview.
NWL | 38844 | 15500

## Allotment
Date | Unit | Resource | Style | PO | Color | Plan_Qty | Optional. Plan pcs ALLOTTED to a machine (Machine_ID) or dry process (Process name) for a date and order. Used by the Capacity page (allotted plan vs capacity vs actual). If empty, the dashboard derives it from the hours the resource ran a style.